## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Light
Implementation and Empirical Evaluation of Pathfinding
Group 14 |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2021-11-03 |  |  |  |  | November | [27 empty] | December
Scrolling Increment: | 0 | time axis 2021-11-03 to 2021-12-28
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2021-11-03 to 2021-12-28
Preparation
Create GitHub Organization | High Risk |  | 0% | 2021-11-03 | 3
Install and Setup VS Code | Med Risk |  | 0% | 2021-11-08 | 1
Install Python 3.9+ | Med Risk |  | 0% | 2021-10-31 | 10
Install PyGame | Med Risk |  | 0% | 2021-11-23 | 1
Install OBS | Low Risk |  | 0% | 2021-11-09 | 6
Research selected pathfinding algorithms | High Risk |  | 0% | 2021-11-11 | 2
Planning
Desing Gui for Testing Environment | Low Risk |  | 0% | 2021-11-09 | 13
Design Testing Strategies | Med Risk |  | 0% | 2021-11-11 | 9
Create desgn for A* algorithm | Med Risk |  | 0% | 2021-11-13 | 11
Create design for Dijkstra's algorithm | Med Risk |  | 0% | 2021-11-15 | 1
Create design for BFS algorithm | Med Risk |  | 0% | 2021-11-16 | 24
Create design for DFS algorihtm | Med Risk |  | 0% | 2021-12-10 | 3
Execution
Implement Test Environment | Med Risk |  | 0% | 2021-11-18 | 4
Implement Testing Strategies | Med Risk |  | 0% | 2021-11-21 | 14
Implement BFS | Med Risk |  | 0% | 2021-12-06 | 6
Implement DFS | Med Risk |  | 0% | 2021-12-07 | 3
Implement A* algorithm | Med Risk |  | 0% | 2021-11-09 | 19
Implement Dijkstra's algorithm | Med Risk |  | 0% | 2021-11-28 | 2
Testing
Testing and recording results | High Risk |  | 0% | 2021-12-10 | 15
Comparison of Algorithms | High Risk |  | 0% | 2021-12-24 | 5
Find external research papers | Milestone |  | 0% | 2021-12-29 | 2
Comparison to external research papers | Goal |  | 0% | 2021-12-31 | 2
Delivery
Final Report | Goal |  | 0% | 2022-01-02 | 2
Video Presentation | Goal |  | 0% | 2022-01-04 | 2
Source Code | Goal |  | 0% | 2022-01-06 | 2
Documentation | Goal |  | 0% | 2022-01-08 | 2
In-person Presentation | Goal |  | 0% | 2022-01-10 | 2
To add more data, Insert new rows ABOVE this one

## Dark
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2021-11-03 |  |  |  |  | November | [27 empty] | December
Scrolling Increment: | 1 | time axis 2021-11-04 to 2021-12-29
Milestone description | Category | Assigned to | Progress | Start | Days | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W
TITLE 1
Task 1 | Goal | Name | 25% | 2021-11-03 | 3 | T: 2; F: 2
Task 2 | Milestone |  |  | 2021-11-08 | 1 | bar: M
Task 3 | Low Risk |  | 50% | 2021-10-31 | 10
Task 4 | Milestone |  |  | 2021-11-23 | 1 | bar: T
Task 5 | Med Risk |  | 10% | 2021-11-09 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2021-11-09 | 13
Task 2 | On Track |  | 50% | 2021-11-11 | 9
Task 3 | Low Risk |  | 33% | 2021-11-16 | 11
Task 4 | Milestone |  |  | 2021-11-18 | 1 | bar: T
Task 5 |  |  |  | 2021-11-19 | 24
TITLE 3
Task 1 | On Track |  |  | 2021-11-18 | 4
Task 2 | Med Risk |  |  | 2021-11-21 | 14
Task 3 | On Track |  |  | 2021-12-06 | 6
Task 4 | Goal |  |  | 2021-12-10 | 3 | F: 2; S: 2; S: 2
Task 5 | Low Risk |  |  | 2021-11-09 | 19
TITLE 4
Task 1 |  |  |  | 2021-12-13 | 15
Task 2 |  |  |  | 2021-12-27 | 5
Task 3 | Milestone |  |  | 2022-02-07 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Color
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2021-11-03 |  |  |  |  | November | [27 empty] | December
Scrolling Increment: | 5 | time axis 2021-11-08 to 2022-01-02
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2021-11-08 to 2022-01-02
TITLE 1
Task 1 | Goal | Name | 25% | 2021-11-03 | 3
Task 2 | Milestone |  |  | 2021-11-08 | 1 | bar: 2021-11-08
Task 3 | Low Risk |  | 50% | 2021-10-31 | 10
Task 4 | Milestone |  |  | 2021-11-23 | 1 | bar: 2021-11-23
Task 5 | Med Risk |  | 10% | 2021-11-09 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2021-11-09 | 13
Task 2 | On Track |  | 50% | 2021-11-11 | 9
Task 3 | Low Risk |  | 33% | 2021-11-16 | 11
Task 4 | Milestone |  |  | 2021-11-18 | 1 | bar: 2021-11-18
Task 5 |  |  |  | 2021-11-19 | 24
TITLE 3
Task 1 | On Track |  |  | 2021-11-18 | 4
Task 2 | Med Risk |  |  | 2021-11-21 | 14
Task 3 | On Track |  |  | 2021-12-06 | 6
Task 4 | Goal |  |  | 2021-12-10 | 3 | 2021-12-10: 2; 2021-12-11: 2; 2021-12-12: 2
Task 5 | Low Risk |  |  | 2021-11-09 | 19
TITLE 4
Task 1 |  |  |  | 2021-12-13 | 15
Task 2 |  |  |  | 2021-12-27 | 5
Task 3 | Milestone |  |  | 2022-02-07 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one